## Issue Log
ID | Module | Unit | Gate | Source | Category | Location | Issue | Root Cause | Resolution | Recurrence | Pipeline Action | Action Status | Pattern #
001 | M7 | U2 | Gate 4 | L1 Checker | Checker Accuracy | §1.8 EC (V4) | V4 checker flags 11 assessment vocab terms as missing from EC dialogue. Terms appear in problem stems/options but not in dialogue-tagged lines. | sp_vocab_scan scans only dialogue-tagged lines, missing terms in surrounding interaction content | Documented as false positive pattern. EC tests skills using these terms without Guide speaking them. | M8 (10 MAJORs), M11 (fixed pre-G4) | Improve sp_vocab_scan to scan full interaction block content, not just dialogue lines | Pending | #27
002 | M7 | U2 | Gate 4 | L2 Agent | Extraction Fidelity | §1.1 / §1.8 EC.1 | §1.1 says EC.1 uses 'dimensions-only with tick marks' but §1.8 defines EC.1 as partial grid. Documentation error. | Backbone description not updated when EC was designed | Revised §1.1 to match §1.8 (partial grid). §1.8 matches TVP. | None | Backbone-to-EC cross-check at Gate 3 | Done | #38
003 | M7 | U2 | Gate 4 | L2 Agent | Pedagogical | §1.7 (2.0→2.1) | Vocabulary-to-application jump needs smoothing — missing scaffolded example between vocab intro and first application | Drafting moved too quickly from vocab to application without Relational bridge | Add scaffolded example between 2.0 and 2.1 | None | None — one-off | Done | #10
004 | M8 | U2 | Gate 4 | L1 Checker | Checker Accuracy | §1.8 EC (V4) | V4 checker flags 10 assessment vocab terms as missing from EC dialogue. Same pattern as M7. | Same root cause as #001 — checker scope too narrow | Documented as false positive. No content change. | M7 (11 MAJORs) | Same as #001 — sp_vocab_scan improvement | Pending | #27
005 | M8 | U2 | Gate 4 | Cross-Layer | Timing | §1.9 Synthesis | L1 estimates Synthesis at 2.5–4.0 min vs 5–7 min target. L2 estimates 4.25–7.5 min (within range). | L1 timing model underweights MC think time and open-response deliberation | No content change. Flagged as L1 calibration issue. | None yet | Improve sp_timing_estimate MC/open-response weighting | Pending
006 | M8 | U2 | Gate 4 | L2 Agent | Pedagogical | §1.9 S.1 | Teaching-only interaction in Synthesis violates Synthesis-as-reflection principle. S.1 presents comparison rather than student recall. | Consolidation modules need side-by-side review that is inherently teaching-adjacent | Accepted as §3H Consolidation Moment exception. Pre-documented and author-approved at Gate 3. | None yet | Document §3H exception pattern — may need a Known Pattern if it recurs | Done
007 | M8 | U2 | Gate 4 | Cross-Layer | Checker Accuracy | §1.9 S.3 | L1 flags S.3 for missing On Correct, non-standard remediation, missing Answer Rationale. L2 flags MC anchoring risk. S.3 is a reflection prompt. | Reflection interactions don't fit standard MC checker expectations | No structural change. Documented as by-design reflection pattern. | None yet | Consider a 'reflection' interaction type that suppresses I7/I8/I9 checks | Pending
008 | M11 | U2 | Gate 4 | L1 Checker | Template Compliance | §1.7 all interactions | All 13 Lesson interactions used bold format instead of H3 headers. Required bulk conversion at Gate 4. | Prior module used as format reference instead of template | Converted all to ### H3 format | M12 (worse — fields as paragraphs) | Pattern #46 (Gate 2 format check) + #48 (template is format authority) | Done | #46, #48
009 | M11 | U2 | Gate 4 | L2 Agent | Template Compliance | §1.10 all KDDs | All 13 KDD entries used bold format instead of H3 headings | Same root cause as #008 — format drift from prior module | Converted all to ### H3 format | None | Same fix as #008 | Done | #48
010 | M11 | U2 | Gate 4 | L1 Checker | Voice | W.4 Guide | 'approach' flagged as red-flag word (assumes knowledge of problem-solving strategies not tracked by system) | Subtle voice anti-pattern — word implies student has a strategy repertoire | Rewrote: 'People approach this kind of problem differently...' → 'There's a faster way to find that. Watch.' | None | None — one-off | Done | #21
011 | M11 | U2 | Gate 4 | Author Review | Pedagogical | §1.9 S.1–S.3 On Correct | Author requested parentheses callback pattern in Synthesis On Correct lines per TVP C-3 requirement | TVP requirement not captured in initial drafting | Added '(__ × __) + (__ × __) = total' callback to S.1, S.2, S.3 | None | Better TVP extraction at Task 1 — C-series requirements easy to miss | Done | #36
012 | M7/M8/M11 | U2 | Gate 4 | L1 Checker | Checker Accuracy | Multiple (DT4/DT5) | Dimension reuse MINORs: M7=8, M8=15, M11=14. All by-design for pedagogical progression. | sp_dimension_track flags all reuse without distinguishing intentional from accidental | Documented as by-design each time. No content changes. | Every module | Add 'intentional_reuse' annotation to suppress known-good dimension reuse | Pending
013 | M11 | U2 | Gate 4 | L1 Checker | Voice | §1.9 S.2 Prompt | Em-dash in Synthesis prompt: 'Three quick vocabulary checks — see below.' | Drafting used em-dash for natural flow; Voice Script prohibits em-dashes in dialogue | Replaced with period: 'Three quick vocabulary checks. See below.' | None | None — one-off | Done | #21
014 | M12 | U2 | Gate 4 | L1 Checker | Template Compliance | §1.1.1, §1.1.3 | Standards Cascade and OUR Lesson Sources used bullet list format instead of table format per template. | Original draft used format from early modules, not template v3 | Converted to table format (Category¦Standard¦Notes and OUR Lesson¦Content Used¦Adaptation Notes) | None | Template v3 tables are easy to miss — consider adding to Gate 2 spot-check | Done | #48
015 | M12 | U2 | Gate 4 | L1 Checker | Template Compliance | §1.7 Purpose Frame | Lesson Purpose Frame written as prose paragraph instead of interaction field structure (Purpose, Visual, Guide, No student action). | Drafting treated Purpose Frame as a narrative intro, not as a structured interaction block | Restructured to interaction field format per template lines 492–499. Prose moved to Design Note blockquote. | None | Add Purpose Frame format to Gate 2 spot-check | Done | #46, #48
016 | M12 | U2 | Gate 4 | L1 Checker | Template Compliance | Design Notes, Success Criteria, Verification Checklist | Three sections used H2 headings (## DESIGN NOTES, ## SUCCESS CRITERIA, ## VERIFICATION CHECKLIST) instead of H3. | Heading hierarchy rules not followed — H2 used within phases where only H3 is allowed | Converted all to H3: ### Design Notes & Voice Notes, ### 1.7.5 Success Criteria, ### Verification Checklist | M11 (interaction headers) | Same root cause — Pattern #48. Template v3 heading hierarchy section should catch this. | Done | #46, #48
017 | M12 | U2 | Gate 4 | L1 Checker | Template Compliance | END marker | END marker had bold formatting: # **END OF MODULE 12 STARTER PACK** — caused ST8 MAJOR. | Bold on H1 headings — template prohibits this but it's a subtle rule | Removed bold: # END OF MODULE 12 STARTER PACK | None | None — one-off formatting error | Done | #46
018 | M12 | U2 | Gate 4 | L2 Agent | Template Compliance | §1.6 Warmup | Missing Warmup Type Rationale subsection between Core Purpose and Parameters. | Section not present in prior module's warmup — template requirement missed | Added ### Warmup Type Rationale with type, rationale, and 5-type rejection analysis | None | Add Warmup Type Rationale to Task 2 requirements extraction checklist | Done | #5, #48
019 | M12 | U2 | Gate 4 | Author Review | Process | §1.7 Interactions 3.5, 3.6 | Two Lesson interactions were still placeholder stubs at Gate 3→4 transition. Had to be fully populated during fix cycle. | Complex module (13 KDDs, 15+ lesson interactions) pushed against context/session limits | Populated 3.5 (L-shaped patio) and 3.6 (U-shape) with full content, dimensions verified unique | None | Pattern #49 (one rolling file) helps. For complex modules, may need to flag incomplete interactions as CRITICAL at Gate 3. | Done
020 | M12 | U2 | Gate 4 | L2 Agent | Template Compliance | §1.10 KDDs | KDD entries used numbered list format instead of ### H3 headings. | Same root cause as M11 — format from prior module, not template | Noted as condition. Needs conversion to H3 heading format. | M11 (13 KDD entries) | Same as #009 — Pattern #48 | Pending | #48
021 | M12 | U2 | Gate 4 | L1 Checker | Timing | §1.9 Synthesis, Full SP | Synthesis estimated at 2.7–4.5 min (target 5–7). Total 14.0–26.3 min (target 25–30). Text-only heuristic. | Same root cause as M8 (#005) — timing model doesn't account for animation, think-time, toy manipulation | Documented as by-design. Conservative text-only estimate. | M8 (Synthesis timing) | Same as #005 — sp_timing_estimate needs updated weighting | Pending
022 | M12 | U2 | Gate 4 | L1 Checker | Checker Accuracy | §1.7 (15 interactions) | I21 flags 15 Lesson interaction Purpose fields as too long (4–9 sentences vs max 3). | Rich pedagogical context in Purpose fields exceeds checker's sentence-count threshold | Documented as by-design. Complex module interactions need detailed Purpose fields. | None at this scale | Consider raising I21 threshold or adding 'complex_module' flag to suppress | Pending
023 | M12 | U2 | Gate 4 | L1 Checker | Checker Accuracy | §1.5 / Visual: fields | TC2 flags Equation Builder in §1.5 but not in Visual: lines. It's referenced in interaction scripts, not Visual field. | Equation Builder is a system tool, not a visual toy — checker doesn't distinguish | Documented as by-design. | None | Consider adding 'system_tool' category to sp_toy_consistency to distinguish visual toys from system tools | Pending
024 | M14 | U2 | Gate 4 | L2 Agent | Cross-Module | M13→M14 bridge | M13 Synthesis promises dependency chain exploration in M14; M14 defers it (KDD-1). | Cross-module bridge creates obligation M14's Section Plan doesn't address | Author decision: soften M13 promise OR add retrospective in M14 Synthesis | NEW — first cross-module promise gap | Add PE1.6 check to m42-pedagogy-eval Gate 1 | Done
025 | M14 | U2 | Gate 4 | L2 Agent | Documentation | §1.8/KDD-8 | Error isolation trade-off rationale incomplete in KDD-8. | KDD documents the decision but not the learning trade-off | Add 1-2 sentences to KDD-8 | None | None needed — content issue | N/A
026 | M14 | U2 | Gate 4 | L1 Checker | Checker Accuracy | Full SP (16 MAJORs) | All 16 L1 MAJORs triaged as non-actionable (guardrails + dimension tables by-design for capstone). | Checkers calibrated for standard CRA modules, not capstone/application modules | Triage as by-design. Added Known Pattern #53. | M7 (V4 false positives), M8 (same) | Added Pattern #53. Consider --module-type flag. | Done | 53
027 | M14 | U2 | Gate 4 | L2 Agent | Process | Working Notes | No Playbook Requirements Checklist section in Working Notes (RQ-1). | Drafting chat didn't operationalize Pattern #5 | Add checklist section to Working Notes | None yet — first module with requirements-eval agent | Enforce #5 at Task 1 in guidance doc | Pending | 5
028 | M14 | U2 | Gate 4 | Author Review | EC Design | §1.8, EC.2a/2b | EC.2a (6×2=12) and EC.2b (4×3=12) produce identical correct answer. Diagnostic value lost. | TVP lists both as options; no checker validates EC answer uniqueness | Swap dresser for rug (5×4=20). Added Known Pattern #54. | NEW — first time caught | Added DT6 check to sp_dimension_track + Pattern #54 | Done | 54
029 | M14 | U2 | Gate 4 | L2 Agent | Voice | §1.7, multiple | 4 voice findings: abrupt On Correct (2.1), flat Purpose Frame (S1), clinical capstone landing (S3), explain-before-observe (2.3). | Voice polish items typical of first-pass drafting | Author fixes per priority list | Similar to M8 voice findings | None needed — content issue | N/A

## Recurring Patterns
Pattern | Occurrences | Modules | Root Cause | Pipeline Action | Status | Priority
L1 false positives for capstone/application modules (V4, ST6, DT3/DT4) | 4+ (M7, M8, M11, M14) | M7, M8, M11, M14 | Checkers calibrated for standard CRA modules; capstone modules legitimately deviate | Added Pattern #53. Consider --module-type capstone flag. | Partial | High
Dimension reuse noise (by-design MINORs) | 3+ (every module) | M7, M8, M11 | Checker cannot distinguish intentional from accidental reuse | Add intentional_reuse annotation support | Pending | Medium
Interaction header format drift (bold → H3) | 4+ (M11, M12 headers + KDDs) | M11, M12 | Prior module used as format reference | Pattern #46 (Gate 2 check) + #48 (template authority) | Done | High
L1 timing underestimates for MC/open-response | 2 (M8, M12) | M8, M12 | Timing model underweights student think time | Improve sp_timing_estimate weighting | Pending | Medium
Teaching-only in Synthesis (§3H exception) | 1 (M8) | M8 | Consolidation modules require teaching-adjacent review | Document as recurring pattern if it appears again | Watch | Low
Reflection MC checker false positives | 1 (M8) | M8 | Reflection interactions don't fit standard MC checker expectations | Consider 'reflection' interaction type flag | Pending | Medium
Template compliance bulk fixes at Gate 4 | 2+ (M11, M12) | M11, M12 | Format drift compounds across modules — prior module used as format reference | Gate 2 spot-check (Step 2b) + Pattern #46/#48. Template v3 addresses format spec. | Done | High
Purpose field length exceeds checker threshold | 1 (M12 — 15 interactions) | M12 | Complex modules need richer Purpose fields than checker allows | Consider raising I21 threshold or adding complexity flag | Pending | Low
KDD format drift (numbered list vs H3) | 2 (M11, M12) | M11, M12 | KDD heading format not enforced during drafting — caught only at Gate 4 | Add KDD format to Gate 2 spot-check or Gate 3 checklist | Pending | Medium
EC items with identical correct answers | 1 (M14) | M14 | No checker validates EC answer uniqueness across sub-items | Added DT6 check to sp_dimension_track + Pattern #54 | Done | Medium
Playbook Requirements Checklist missing from Working Notes | 1 (M14) | M14 | Drafting chat skips operationalizing Pattern #5 | Reinforce #5 at Task 1 setup. m42-requirements-eval catches at Gate 4. | Pending | Medium
Cross-module bridge promises not addressed by next module | 1 (M14) | M14 | M[X-1] Synthesis makes forward promises that M[X] Section Plan doesn't address | Added PE1.6 check to m42-pedagogy-eval Gate 1 | Done | High

## Postmortem Log
Date | Scope | New Issues Since Last | Recurring Issues | Pipeline Actions Taken | New Patterns Added | Checker Updates | Notes
2026-04-01 | U2 M7–M11 + U5 M1–M2 | 13 | 3 | Template v3 created (format drift fix). Known Patterns restructured to gate-scoped shortlists. Gate 2 spot-check + Gate 4 compliance audit added. Pattern #52 (Options not in Prompt) added. | #46, #47, #48, #49, #50, #51, #52 | Pending: sp_vocab_scan scope expansion, sp_timing_estimate MC weighting, sp_dimension_track annotation support | First postmortem. Seeded tracker from 5 Gate 4 reports (M7, M8, M11, U5-M1, U5-M2). Established baseline.